## Sheet1
Task# | Name | Start Date | End Date | #days long | %Done | Owner | Priority | Depend On
t1 | IP Brainstorming | Mar 3, 20 |  | 14 | 100 | Garry, Mi
t2 | ID writing | Mar 16, 20 |  | 21 | 100 | Garry
t3 | IP filing |  |  | 20 | 100 | Ryan |  | t2
m1 | Finish background IP | [6 empty] | t3, m2
t4 | JDA GLW revision to BOE | Mar 1, 20 |  | 31 | 100 | Ryan
t10 | BOE revision to GLW |  |  | 20 | 100 | Tom |  | t4
t13 | GLW 2nd revision |  |  | 10 | 100 | Ryan |  | t10
t14 | BOE 2nd revision |  |  | 10 | 100 | Tom |  | t13
t11 | GLW final review |  |  | 10 |  | Ryan |  | t14
t12 | BOE final review |  |  | 10 |  | Tom |  | t11
m2 | JDA draft compelte | [6 empty] | t12
t15 | Get lab access and prework done | Apr 15, 2020 |  | 20 | 100 | Mi
t6 | BLU components shipping to SP | May 10, 2020 |  | 15 | 80 | Tom
t8 | Prepare PGD, assemble BLU |  |  | 7 |  | Mi |  | t6,t15
t7 | Work on 27in glass | Mar 1, 20 |  | 30 | 100 | Mi
t9 | send BLU to BJ |  |  | 7 |  | Mi |  | t8
m3 | Hold BLU to BOE till JDA effective | [6 empty] | t9, m2