## Sheet1
Task# | Name | Start Date | End Date | #days long | %Done | Owner | Priority | Depend On
t1 | IP Brainstorming | Mar 3, 20 |  | 14 | 100 | Garry, Mi
t2 | ID writing | Mar 16, 20 |  | 21 | 30 | Garry | High
t3 | IP filing |  |  | 10 | 0 | Ryan | High | t2
m1 | Finish background IP | [6 empty] | t3, m2
t4 | JDA GLW revision to BOE | Mar 1, 20 |  | 20 | 100 | Ryan
t10 | BOE revision to GLW |  |  | 7 |  | Tom |  | t4
t11 | GLW final review |  |  | 7 |  | Ryan |  | t10
t12 | BOE final review |  |  | 7 |  | Tom |  | t11
m2 | JDA draft compelte | [6 empty] | t12
t6 | BLU components shipping to SP | Mar 30, 20 |  | 7 |  | Tom
t8 | BLU assembly |  |  | 7 |  | Mi |  | t6
t7 | Work on 27in glass | Mar 1, 20 |  | 30 | 70 | Mi
t9 | send BLU to BJ |  |  | 7 |  | Mi |  | t8
m3 | Hold BLU to BOE till JDA effective | [6 empty] | t9, m2